## Gantt chart
This timeline is a very simplified example, you will need to adjust it to your specific needs.
Downloading a template is nice, but would you like to discuss with a real person about your PhD timeline? Contact me now = September/October 2026 if you would like to benefit from PhD coaching at an affordable price!
I am currently undertaking training to become a certified coach and to pass the certification I need to practise coaching with clients => a win-win opportunity! Check my web page and contact me soon!
https://academiac.net/coaching/
year | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
month | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
reading | read literature
Project design | Develop methods, protocol design, explore projects
Committee Meeting | [11 empty] | CM | Submit
Experiments | [12 empty] | perform experiments on main project 1
Writing paper | [21 empty] | write paper 1 | [7 empty] | Paper revision
Committee Meeting | [23 empty] | CM
Experiments | [24 empty] | perform experiments on main project 2
Writing paper | [34 empty] | write paper 2 | [5 empty] | Paper revision
Attend conference | [27 empty] | IC
Committee Meeting | [35 empty] | CM
Writing thesis and preparing your defense | [42 empty] | Write thesis |  |  |  | Graduation
| Reading |  |  |  |  | CM = Committee Meeting = time to review your timeline and refine it | [10 empty] | Literature reading is likely to be heavier in the first year but will still be important throughout the doctoral process.
| Method | [15 empty] | The IC is put here at a relative random time to serve as a reminder of something one might want to consider for the yea 3 or 4.
| Experiments |  |  |  |  | IC = International Conference | [10 empty] | Some tasks can be performed in parallel, like finishing up some experiments while writing a paper.
| Papers |  |  |  |  | Milestone
Graduation
from https://academiac.net/2018/11/20/guidelines-to-draw-a-timeline-of-your-phd/