## Gantt chart
Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01 | 2016-05-01 | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01
read literature
Develop method, protocol design, explore projects
[11 empty] | CM | Submit
perform experiments on main project
CM
sketch paper draft
perform experiments on main project
CM
[34 empty] | write main paper | [5 empty] | Paper revision
[29 empty] | IC | [12 empty] | Write thesis |  |  |  |  | Graduation
Reading |  |  |  |  | CM = Committee Meeting = time to refine project plans | [10 empty] | Literature reading is likely to be heavier in the first year but will still be important throughout the doctoral process
Method | [15 empty] | Tasks like “perform experiments” were cut in different rows to give a higher sense of flow
Data acquisition |  |  |  |  | IC = International Conference | [10 empty] | The IC is put here at a relative random time to serve as a reminder of something one might want to consider for year 3 or 4
Papers |  |  |  |  | Milestone | [10 empty] | Some tasks can be performed in parallel, like finishing up some experiments while writing a paper
Graduation | [15 empty] | This timeline is only an example and is not designed with any specific project in mind, you will need to adjust it to your specific needs
from https://academiac.net/2018/11/20/guidelines-to-draw-a-timeline-of-your-phd/